## Sheet1
2020年度市级财政支出项目绩效再评价评分表
项目名称 | 实验室建设 |  | 单位名称 | 苏州市农业科学院
内容 | 指标名称 | 权重 | 评分结果 | 备注
投入目标(24 分) | 资金使用合规性 | 3 | 3
| 财务制度健全性 | 3 | 3
| 资产产权明确性 | 1 | 1
| 各级财政应承担资金到位率 | 1 | 1
| 预算执行率 | 8 | 8
| 专款专用率 | 3 | 3
| 资金节约率 | 1 | 1
| 政府采购规范性 | 2 | 2
| 可行研究充分性 | 1 | 1
| 工程变更合规性 | 3 | 3
产出目标 (24 分) | 采购完成率 | 4.8 | 4.8
| 设备与可行性报告相符性 | 4.8 | 4.8
| 设备验收通过率 | 4.8 | 4.8
| 工程完成率 | 4.8 | 0 | 目标值100%，实际完成值78.26%
| 购置设备23台 | 4.8 | 4.8
结果目标(26 分) | 设备年底投入使用率 | 7.33 | 2.55
| 设备使用满意度 | 7.33 | 0 | 目单位在新购仪器使用情况调查表中对采购设备满意度只做了简单的打分，无法认定
| 检测结果 | 7.34 | 0 | 目标值≥1000个，实际完成值70个
影响力目标(6 分) | 科研设备制度健全性 | 2.67 | 2.67
| 仪器设备人员配套率 | 2.67 | 2.67
| 实验室管理制度健全性 | 2.66 | 2.66
指标质量 |  | 4 | 2.4
报告质量 |  | 12 | 6 | 报告存在以下不足：项目概况总体描述不够完整，项目年度目标不明确，项目管理存在的问题及原因缺少从投入到产出和效果的逻辑分析以及其中产生的项目管理方面的问题，缺少对扣分项的问题及原因描述。
组织管理工作 |  | 4 | 4
合计 |  | 100 | 68.15
Note on A4: type
Note on A14: type
Note on A19: type
Note on A22: type
Note on B4: t_type
Note on B5: t_type
Note on B10: t_type
Note on B11: t_type
Note on B14: c_type
Note on B15: c_type
Note on B16: c_type
Note on B19: j_type
Note on B20: j_type
Note on B21: j_type
Note on B22: y_type
Note on B23: y_type
Note on D4: index_reevalua_score
Note on D5: index_reevalua_score
Note on D10: index_reevalua_score
Note on D11: index_reevalua_score
Note on D14: index_reevalua_score
Note on D15: index_reevalua_score
Note on D16: index_reevalua_score
Note on D19: index_reevalua_score
Note on D20: index_reevalua_score
Note on D21: index_reevalua_score
Note on D22: index_reevalua_score
Note on D23: index_reevalua_score
Note on D25: index_quality
Note on D26: report_quality
Note on E4: remark_item
Note on E5: data_source
Note on E7: remark_item
Note on E10: remark_item
Note on E11: remark_item
Note on E14: remark_item
Note on E15: remark_item
Note on E16: remark_item
Note on E19: remark_item
Note on E20: remark_item
Note on E21: remark_item
Note on E22: remark_item
Note on E23: remark_item